## Sheet1
Phase/Sprint	Task ID	Task	Allocated to	Planned Start Date	Planned End Date	Status	Notes
Week 1	1	form groups	group	23/09/2024	30/09/2024	x	-
	2	project initiation	group	23/09/2024	30/09/2024	x	x
Week 2	3	define scope	group	30/09/2024	07/10/2024	x	x
	4	initial project plan	group	30/09/2024	07/10/2024	x	x
Week 3	5	c4 model level 1 & 2	raf	07/10/2024	14/10/2024	x	could do with further improvements such as using more different types of users
	6	start recording architectural descision records	group	07/10/2024	14/10/2024		“working document”
	7	create wireframes	flinn	07/10/2024	14/10/2024		low fidelity wireframes complete, high fidelity wireframes need completing
Week 4	8	create use case diagrams	veronica	14/10/2024	21/10/2024	x	x
	9	create component diagrams	raf	14/10/2024	21/10/2024
	10	update architectural decision records	group	14/10/2024	21/10/2024
Week 5	11	refine conceptual model	raf	21/10/2024	28/10/2024
	12	update architectural decision records	group	21/10/2024	28/10/2024
Week 6	13	refine design to apply software architecture style	flinn	28/10/2024	04/11/2024
Week 7	14	refine design to include the use of appropriate patterns	group	04/11/2024	11/11/2024
	15	plan sprint 1	group	04/11/2024	11/11/2024
Week 8	16	create data design	veronica	11/11/2024	18/11/2024
	17	update architectural decision records	group	11/11/2024	18/11/2024
	18	start sprint 1	group	11/11/2024	18/11/2024
Week 9	19	sprint 1 review and retrospective	group	18/11/2024	25/11/2024
	20	refine design if needed	group	18/11/2024	25/11/2024
	21	plan sprint 2	group	18/11/2024	25/11/2024
Week 10	22	start sprint 2	group	25/11/2024	02/12/2024
	23	refine design if needed	group	25/11/2024	02/12/2024
	24	update architectural decision records	group	25/11/2024	02/12/2024
Week 11	25	system testing and result documentation	group	02/12/2024	09/12/2024
	26	sprint 2 review and retrospective	group	02/12/2024	09/12/2024
	27	prepare user evalutation plan	group	02/12/2024	09/12/2024
Week 12	28	project wrap up and finalise required documentation	group	09/12/2024	16/12/2024
Week 13	29	submission of task 1 & 2 by 19/12/2024 15:00	group	16/12/2024	19/12/2024